## Milestone 2
Topic |  |  |  | Requires Code Sample | Blocked | Priority | Written | Copy Edited | Tech Reviewed | Committed | Completed | Location | Notes
HBase
| Introduction: HBase in HDInsight | [9 empty] | Y | hdinsight-hbase-overview | Covered in hdinsight-hbase-overview
|  | Use cases and when to use | [8 empty] | Y | hdinsight-hbase-overview | Covered in hdinsight-hbase-overview
| Choosing underlying storage for Hbase (WASB and ADLS) | [5 empty] | Y |  |  |  |  | hdinsight-hbase-storage-options.md
| Using Hbase Shell | [9 empty] | Y | hdinsight-hbase-tutorial-get-started-linux | Covered in hdinsight-hbase-tutorial-get-started-linux
| Using Hbase REST SDK | [5 empty] | Y |  |  |  |  | hdinsight-using-hbase-rest-sdk.md
| Access Hbase table with Hive |  |  | Y | [6 empty] | Y | hdinsight-hbase-tutorial-get-started-linux | Covered in hdinsight-hbase-tutorial-get-started-linux
| Setup Hbase backup and replication | [5 empty] | Y |  |  |  |  | hdinsight-hbase-backup-replication.md | Replication is covered in hdinsight-hbase-replication
| Read/write HBase data from Spark cluster | [5 empty] | Y |  |  |  |  | hdinsight-using-spark-to-query-hbase.md
| Securing HBase with Ranger and AAD | [9 empty] | Y |  | Skip as this is not yet supported.
| Monitoring HBase with OMS |  |  | Y |  |  | Y
| HBase performance Best Practices | [9 empty] | Y |  | Suggest pulling in content from https://blogs.msdn.microsoft.com/azuredatalake/2016/09/02/hdinsight-hbase-9-things-you-must-do-to-get-great-hbase-performance/
Phoenix
| Introduction: Phoenix in HDInsight | [5 empty] | Y |  |  |  |  | hdinsight-phoenix-in-hdinsight.md
| Get Started with Phoenix in HDInsight |  |  |  | Y |  | y |  |  |  |  | hdinsight-hbase-phoenix-squirrel-linux.md | Propose we rename this file since SQLLine is coverred and squirrel is not
| Interacting with Phoenix via pysql |  |  | Y |  |  | Y |  |  |  |  | hdinsight-phoenix-psql.md
| Using Phoenix Query Server REST SDK |  |  | Y |  |  | Y |  |  |  |  | hdinsight-using-phoenix-query-server-rest-sdk.md
| Setup Phoenix Backup and Replication | [5 empty] | Y |  |  |  |  | hdinsight-hbase-backup-replication.md | Backup/replication of Phoenix is covered in this article as well.
| Read/Write Phoenix data from Spark cluster |  |  |  | Y |  | Y | [5 empty] | Need confirmation if using Phoenix from Spark is really supported. Documentation indicates it is not. Do we cut?
| Securing Phoenix with Ranger and AAD | [9 empty] | Y |  | Skip as this is not yet supported.
| Phoenix performance best practices | [5 empty] | Y |  |  |  |  | hdinsight-hbase-phoenix-performance.md
Optimizing Hive Job Performance
| Optimizing Hive Job Performance | [5 empty] | Y |  |  |  |  | hdinsight-changing-configs-via-ambari.md
Optimizing and configuring Spark Jobs for Performance
| Optimizing and configuring Spark Jobs for Performance | [5 empty] | Y
|  | Choosing configuration for your Spark application (Executor memory, number of executors, number of executor cores etc.) |  |  |  |  | Y
|  | Optimizing performance of your Spark jobs |  |  |  |  | Y
|  | Optimizing performance of your SparkSQL jobs |  |  |  |  | Y
| Choosing between Dataset and Dataframe and RDD API | [5 empty] | Y |  |  |  |  | hdinsight-spark-rdd-vs-dataframe-vs-dataset.md
Apache Open Source Ecosystem
| ISV apps - Edge node | [5 empty] | Y |  |  |  |  | hdinsight-apps-install-applications.md
|  | H2O |  |  |  |  | Y |  |  |  |  | hdinsight-install-published-app-h2o.md
|  | Datameer |  |  |  |  | Y |  |  |  |  | AND hdinsight-install-published-app-datameer.md
|  | Streamsets |  |  |  |  | Y |  |  |  |  | hdinsight-install-published-app-streamsets.md
|  | AtScale |  |  | Y | P0 | [6 empty] | blocked getting access
|  | Dataiku | [8 empty] | Y |  | Already covered by https://azure.microsoft.com/en-us/blog/introducing-dataiku-s-dss-on-microsoft-azure-hdinsight-to-make-data-science-easier/
|  | Cask | [8 empty] | Y |  | Already covered by https://blogs.msdn.microsoft.com/azuredatalake/2016/10/17/using-cask-data-application-platform-on-azure-hdinsight/
|  | Talena |  |  | Y | P1 | [6 empty] | blocked waiting for Talena to post instructions in about a month
Advanced Scenarios (Deep Dive)
| ETL at Scale |  |  |  |  | P0 | [6 empty] | Update content from https://msdn.microsoft.com/en-us/library/dn749842.aspx
|  | "" |  |  |  | P0
|  | "" |  |  |  | P0
| Data Warehouse on Demand |  |  |  |  | P2 | [6 empty] | Update content from https://msdn.microsoft.com/en-us/library/dn749783.aspx
| Iterative Data exploration |  |  |  |  | P1 | [6 empty] | Update content from https://msdn.microsoft.com/en-us/library/dn749877.aspx
| Streaming and BI |  |  |  |  | P0
|  | "" |  |  |  | P0
|  | "' |  |  |  | P0 | [6 empty] | Update content from https://msdn.microsoft.com/en-us/library/dn749881.aspx
| Running batch & interactive with Hadoop and Spark |  |  |  |  | P2
| Running Custom Programs and Workloads on HDInsight |  |  |  | Y | [7 empty] | Is there a specific custom program we should focus on?
ML
| Advanced Analytics |  |  |  |  | P0
|  | "" |  |  |  | P0
|  | "" |  |  |  | P0
| Operationalizing the Big Data Pipeline - ADF, Oozie, etc. |  |  |  |  | P0
|  | "" |  |  |  | P0
|  | "" |  |  |  | P0
| Backup |  |  |  | Y | [7 empty] | Can we combine these Backup and DR into a single article?
| DR |  |  |  | Y
| Lambda Architecture |  |  |  |  | P1
Advanced Configuration (P0 – merge with chapter on cluster configuration)
| Network - VNET, Custom VNET, Static IP | [5 empty] | Y |  |  |  |  | hdinsight-extend-hadoop-virtual-network.md
| SSH Connectivity |  |  |  | Y | [5 empty] | Y |  | How is this different from hdinsight-hadoop-linux-use-ssh-unix and hdinsight-linux-ambari-ssh-tunnel? Anything else that needs to be covered?
| Dynamic port forwarding |  |  |  | Y | [5 empty] | Y |  | Is this for use in SSH tunneling or for what scenario?
| Save IT Cost - create cluster during day and delete during night and reuse metastore | [5 empty] | Y |  |  |  |  | hdinsight-lifecycle-of-an-hdinsight-cluster.md | Covered in hdinsight-lifecycle-of-an-hdinsight-cluster.md
|  | Azure Automation |  |  |  |  | Y |  |  |  |  | hdinsight-lifecycle-of-an-hdinsight-cluster.md | Covered in hdinsight-lifecycle-of-an-hdinsight-cluster.md
|  | Scripts |  |  |  |  | Y |  |  |  |  | hdinsight-lifecycle-of-an-hdinsight-cluster.md | Covered in hdinsight-lifecycle-of-an-hdinsight-cluster.md
|  | ADF |  |  |  |  | Y |  |  |  |  | hdinsight-lifecycle-of-an-hdinsight-cluster.md | Covered in hdinsight-lifecycle-of-an-hdinsight-cluster.md
| Scaling - Best Practices |  |  |  |  | P0
Cluster state
Scale down implications
Extending HDInsight to on-Prem cluster (P0)
| Extending HDInsight to an on-premise cluster |  |  |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
|  | Express route |  |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
|  |  | Connecting on on-prem resource vie Express Route |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
|  |  | Connecting On-prem DNS Server with Express Route (ProTip: We have to figure out what ports to open etc.) |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
|  | Firewalls |  |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
|  | Open ports |  |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
Hybrid Cloud Scenarios (P0)
| Synchronize On-prem Data/Metadata with Cloud |  |  |  | Y | P1 | [6 empty] | We will need materials on these... Does engineering team have notes/guidance we can start from?
Enterprise Scenarios (P0)
| Composing multiple HDInsight clusters in a Virtual Network | [9 empty] | Y | hdinsight-extend-hadoop-virtual-network | Covered in hdinsight-extend-hadoop-virtual-network
Data Ingestiion to Azure blob (P0)
| Ingestion of HDFS data from on-prem to lcuster | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
| Ingestion using Flume | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
| Ingestion using Sqoop | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
| What tools to use for GUI, e.g., CloudXplorer | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
Data Ingestion to ADLS (P0)
| Ingestion of HDFS data from on-prem cluster | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
| Intestion using Flume | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
| What tools to use for GUI, e.g., CloudXplorer | [5 empty] | Y |  |  |  |  | hdinsight-upload-data | Covered in hdinsight-upload-data
Troubleshooting
| Job Debugging (specific for each workload - MR, Hive, Spark) |  |  |  |  | P0
Where to get logs?
Where are my logs stored?
How long are they stored?
Configurable?
| How to configure Splunk/DataDog for log ingestions with HDInsight |  |  |  |  | P0
| Use WASB for storing scratch data (instead of local disks) |  |  |  | Y | P0 | [6 empty] | Should this guidance be a part of the hdinsight-architecture article, in the section on storage? What's the reasoning here?
| Debugging using Ambari Hive views | [9 empty] | Y | hdinsight-debug-ambari-tez-view | Already covered in hdinsight-debug-ambari-tez-view
| Hive troubleshooting | [11 empty] | The idea is to cover all necessary debugging and troubleshooting steps. There are some captured here https://docs.microsoft.com/en-us/azure/hdinsight/hdinsight-hadoop-linux-information but it doesn’t cover all the scenario. You can also refer EMR developer guide and management guide on different aspects that are covered to ensure what else we can add. http://docs.aws.amazon.com/emr/latest/ManagementGuide/emr-mgmt.pdf http://docs.aws.amazon.com/emr/latest/DeveloperGuide/emr-dg.pdf
| Spark troubleshooting | [11 empty] | same as above
| Storm troubleshooting | [11 empty] | same as above
| Kafka troubleshooting | [11 empty] | same as above
|  | Monitoring via Kafka metrics | [10 empty] | same as above
| Retention policy for logs and cost of storage for logs |  |  |  |  | P0 | Y |  |  |  |  | hdinsight-log-management.md | changed article name to ‘Managing Logs for HDInsight’
| Performance |  |  |  | Y | [7 empty] | Wouldn’t this be covered in the troubleshooting topics specific to each cluster type or in the Cluster Debugging "troubleshooting a slow cluster"?
Cluster Debugging
| Where to get logs? | [9 empty] | Y |  | Duplicate of the topics in Troubleshooting chapter above per Bhanu.
|  | Where are my logs stored? | [8 empty] | Y |  | Duplicate of the topics in Troubleshooting chapter above per Bhanu.
|  | How long are they stored? | [8 empty] | Y |  | Duplicate of the topics in Troubleshooting chapter above per Bhanu.
|  | Configurable? | [8 empty] | Y |  | Duplicate of the topics in Troubleshooting chapter above per Bhanu.
| Retention policy for logs and cost of stroage for logs |  |  |  |  | P0 |  |  |  |  | Y |  | Duplicate of the topics in Troubleshooting chapter above per Bhanu.
| Common errors |  |  |  |  | P0 |  |  |  |  | Y |  | Duplicate of the topics in Troubleshooting chapter above per Bhanu.
| Troubleshooting a failed cluster (see this guide http://docs.aws.amazon.com/emr/latest/ManagementGuide/emr-mgmt.pdf) |  |  |  |  | P0 | Y |  |  |  |  | hdinsight-troubleshoot-failed-cluster.md
| Troubleshooting a slow cluster (see this guide http://docs.aws.amazon.com/emr/latest/ManagementGuide/emr-mgmt.pdf) |  |  |  |  | P0 |  |  |  |  | Y | hdinsight-troubleshoot-failed-cluster.md | Combined into one article with "Troubleshooting a failed cluster" since there was significant overlap, event in the EMR reference documentation.
Advanced Settings (P0)
Advanced Settings
|  | Hadoop - JVM, Task settings |  |  |  | P1
|  | Hbase |  |  |  | P1
|  | Spark |  |  |  | P1
Storm
Performance Tuning
| Platform |  |  |  | Y | p1 | [6 empty] | Can we get more details on what should be covered here?
| Workload |  |  |  | Y | p1 | [6 empty] | Can we get more details on what should be covered here?
| Scenarios |  |  |  | Y | p1 | [6 empty] | Can we get more details on what should be covered here?
|  |  |  | SUMMARY: | P0 | 22
[5 empty] | P1 | 16

## Milestone 1
Topic |  |  |  | Requires Code Sample | Blocked | Priority | Written | Copy Edited | Tech Reviewed | Committed | Completed | Location | Notes
What is Azure HDInsight
| Iterative Data exploration (P0) |  |  |  |  | P0 | [7 empty] | Needs overview
| Data Warehouse on Demand (P0) |  |  |  |  | P0 | [7 empty] | Needs overview
| ETL at scale (P0) | [5 empty] | Y |  |  |  |  | hdinsight-etl-at-scale.md | Waiting for instructions on how to migrate content. Migrate content for this from P&P site at https://msdn.microsoft.com/en-us/library/dn749877.aspx) | Needs overview
| Streaming at scale (P0) | [5 empty] | Y |  |  |  |  | hdinsight-streaming-at-scale-overview.md
| Machine learning (P0) | [5 empty] | Y |  |  |  |  | hdinsight-machine-learning-overview.md
| Hadoop, Spark Programming (P0) |  |  |  | Y | P0 | [6 empty] | What should be covered? Need more clarification. | Achieving batch & interactive with Hadoop and Spark
| Custom Programs |  |  |  | Y | P0 | [6 empty] | What should be covered? Need more clarification. | MR
| Move data with HDInsight (P0) | [10 empty] | hdinsight-upload-data | Covered by hdinsight-upload-data | add adls, ad distcp, cloudxplorer, flume, change title (upload data to HDInsight), azcopy on linux, pull in content from Sqoop. Update to include ADLS as a target.
Azure HDInsight & Hadoop Architecture (P0)
| Hadoop Architecture – MR, YARN, etc. | [5 empty] | Y |  |  |  |  | hdinsight-hadoop-architecture.md |  | Layer on section on Spark on YARN. Change title to Hadoop + Spark
| HDInsight Architecture | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md |  | add generic arch diagram at intro (see Pranav email), and for the managed disks. Node types table formatting off. Add commentary on why 2 head nodes, 3 zookeeper nodes. Update gateway diagram to show flow. You can have a single data store accessed by multiple clusters- add diagram after metadata storage for shared metadata and storage across multiple clusters. Network architecture - modify diagram to show on-prem/cloud hybrid, rename HDI icons to Hadoop and Spark. Every illustration should read HDInsight (Hadoop & SPark) | We have a seet of supported cluster types ad disccussed in the article. We have a lot of other open source projects we support. If you want to install custom solutions, install them with script actions. | Add Cluster Type of custom. For example Presto, Solr, Hue. | Add header, diagram and paragraph around custom clusters
| Lifecycle of HDI Cluster | [5 empty] | Y |  |  |  |  | hdinsight-lifecycle-of-an-hdinsight-cluster.md |  | link to ADF on-demand article (verify if this works), link to article on Oozie. Diagram of scaling options | **3. Pipe your data to a permenant storage location.** clean up. **4. Tear down the cluster using PowerShell.** you can also use CLI, runbooks, etc. | Sample showing PowerShell scaling according to schedule. | An important consideration: when you create a cluster...as nodes become available they can begin processing. No need to wait for all nodes in the cluster to be ready.
| Lifecycle of a job (User submits job, job runs…etc.) |  |  |  |  | P0 | [5 empty] | hdinsight-hadoop-architecture.md |  | Lifecycle of Spark job, Hive Job
| HDFS | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
| Gateway | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
| Nodes (Head, Worker, Edge) | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
| Worker node | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
| Edge nodes | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
| Zookeeper | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
| High availability model | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md |  | combine with separation of persistence and address in architecture article
| Cluster lifecycle | [9 empty] | Y |  | Duplicate of Lifecycle of HDI Cluster
| Separation of persistence | [5 empty] | Y |  |  |  |  | hdinsight-architecture.md
Capacity Planning | [13 empty] | Change to FAQ with subheading of capacity planning. Best practices in going to production | 1. Benchmark with TPC, start with small cluster, scale out | Pranave will share deck on this | Capacity planning doc
| Choosing the right Region | [5 empty] | Y |  |  |  |  | hdinsight-capacity-planning.md |  | Instead of listing ADLS regions, just put link to regions page in azure.com . Also for Azure Storage | VM types, how to choose series. Dv2 gives 30% than D. | Include Azure Storage Limits
| Choosing right cluster type | [5 empty] | Y |  |  |  |  | hdinsight-capacity-planning.md
| Choosing right VM | [5 empty] | Y |  |  |  |  | hdinsight-capacity-planning.md
| Choosing right number | [5 empty] | Y |  |  |  |  | hdinsight-capacity-planning.md
| Common problems |  |  |  | Y | P0 | [6 empty] | What common problems should we cover here? | Make this the start of an on-going FAQ
Configuring the Cluster (P0)
| Create Hive and Oozie databases* |  |  | Y | [6 empty] | Y | hdinsight-using-external-metadata-stores.md | What should be covered? Not sure how this is different from coverage of metastores in hdinsight-using-external-metadata-stores.md
Management - Ambari
Authorize the users to Ambari
Give permissions to Hive views
To Tez views
Operator Role
Read Only role
| Levearaging the Big Data Ecoystem of | [9 empty] | Y | hdinsight-apps-install-applications | Covered in hdinsight-apps-install-applications | <-move into ecosystem chapter
|  | TBD: Action item for Rashim to define the 3rd party apps | [10 empty] | Marked as TBD, request additional clarification | About 5-6 pages
| Authorize the users to Ranger | [9 empty] | Y | hdinsight-domain-joined-manage | Covered in hdinsight-domain-joined-manage
| Add ACLs for users in Ranger | [9 empty] | Y | hdinsight-domain-joined-manage | Covered in hdinsight-domain-joined-manage
Add ACLs for users at File and Folder storage level
ADLS
|  | WASB |  |  |  | P0
| Advanced* |  |  | Y
|  | Sync other users from AAD to cluster (Ambari + Ranger) | [11 empty] | Bhanu will send PDF instructions on how to sync AAD users with Ranger
|  | Add extra storage accounts to an existing cluster | [8 empty] | Y | hdinsight-hadoop-add-storage | Covered in hdinsight-hadoop-add-storage
|  | Add extra SSH users to an existing cluster |  |  | Y | P1 | [7 empty] | Bhanu will clarify
|  | Save meta store for future use | [8 empty] | Y | hdinsight-using-external-metadata-stores.md | Covered in hdinsight-using-external-metadata-stores.md
|  | Suppress / control updates to the OS patches |  |  |  | P1
|  | Control reboots |  |  | Y | P1
| Cluster creation using ADF* |  |  |  | Y | P0 |  |  |  |  | Y | hdinsight-hadoop-create-linux-clusters-adf | Covered in hdinsight-hadoop-create-linux-clusters-adf. ADF team needs to update ARM template to remove hardcoding to HDI 3.2, otherwise it tested out fine. | Try out the ADF one?
|  | Sample scripts in GitHub | [8 empty] | Y | hdinsight-hadoop-create-linux-clusters-adf | "
|  | Best practices | [8 empty] | Y | hdinsight-hadoop-create-linux-clusters-adf | "
|  | Limitations | [11 empty] | Domain join doesn't work…need to validated. Should work for Spark with LIVY
Monitoring and managing the cluster
| What scenarios to monitor and how to do it? | [5 empty] | Y |  |  |  |  | hdinsight-key-scenarios-to-monitor.md
|  | Is the cluster well utilized or under heavy/light load? |  |  |  |  | Y |  |  |  |  | hdinsight-key-scenarios-to-monitor.md
|  | Are the YARN queues properly configured? |  |  |  |  | Y |  |  |  |  | hdinsight-key-scenarios-to-monitor.md
|  | Is there any storage throttling happening? |  |  |  |  | Y |  |  |  |  | hdinsight-key-scenarios-to-monitor.md
| Ambari server | [9 empty] | Y | See details below
|  | Rest APIs* |  | Y | [6 empty] | Y | hdinsight-hadoop-manage-ambari-rest-api | Covered in hdinsight-hadoop-manage-ambari-rest-api
|  | Provide a full list of available REST APIs to customers so that they can do their own monitoring | [8 empty] | Y | hdinsight-hadoop-manage-ambari-rest-api | Covered in hdinsight-hadoop-manage-ambari-rest-api
|  | Ambari alerts | [8 empty] | Y | hdinsight-hadoop-manage-ambari | Covered in hdinsight-hadoop-manage-ambari
|  | Ambari metrics | [8 empty] | Y | hdinsight-hadoop-manage-ambari | Covered in hdinsight-hadoop-manage-ambari
|  | Start/Stop services* |  | Y | [7 empty] | hdinsight-hadoop-manage-ambari | Coverd in hdinsight-hadoop-manage-ambari | sample using alerts, metrics and start/stop services
| Management? Refer the operations from here https://docs.microsoft.com/enus/ azure/hdinsight/hdinsight-administer-use-portal-linux | [5 empty] | Y |  |  |  |  | hdinsight-administer-use-portal-linux.md |  | can you resize while a script action is running? Need to capture the you cannot.
| Changing configs via Ambari | [5 empty] | Y |  |  |  |  | hdinsight-changing-configs-via-ambari.md
| Adding storage accounts after cluster creation | [9 empty] | Y | hdinsight-hadoop-add-storage | Covered in hdinsight-hadoop-add-storage
| Script Actions (ProTip: All changes via ScriptActions an no ad-hoc changes)* | [9 empty] | Y | hdinsight-hadoop-customize-cluster AND hdinsight-hadoop-script-actions | Covered in hdinsight-hadoop-customize-cluster AND hdinsight-hadoop-script-actions
|  | How to configure and administer OS Patching (Follow up: Andy) | [8 empty] | Y |  | What should be covered? Need more details. | They will send the doc that they have. What level of patching is covered as part of the Managed experience
|  | Antivirus | [8 empty] | Y |  | What should be covered? Need more details. | Skip
|  | Scriptactions during and after cluster creation | [8 empty] | Y | hdinsight-hadoop-script-actions | Covered in hdinsight-hadoop-script-actions
Developing Hive apps (Using Hadoop for ETL) (P0)
| Hive, ETL overview | [5 empty] | Y |  |  |  |  | hdinsight-using-apache-hive-as-an-etl-tool.md
| Configuring Hive, Configure JDBC/ODBC | [9 empty] | Y | hdinsight-connect-hive-jdbc-driver | Coverd in hdinsight-connect-hive-jdbc-driver
| Externalize metastore (link common operations) | [5 empty] | Y |  |  |  |  | hdinsight-using-external-metadata-stores.md
| Writing Hive application using Java, Python | [9 empty] | Y |  | Covered in hdinsight-hadoop-hive-java-udf AND hdinsight-python.
| UDFs | [9 empty] | Y | hdinsight-hadoop-hive-java-udf AND hdinsight-hadoop-hive-pig-udf-dotnet-csharp | Covered in hdinsight-hadoop-hive-java-udf AND hdinsight-hadoop-hive-pig-udf-dotnet-csharp
| Configuring Hive settings |  |  |  |  | P0 | [6 empty] | What should be covered? Need more details. | opt perf, for batch do this, for interactive do that.
| Using JSON SerDe* |  |  | Y | [6 empty] | Y | hdinsight-using-json-in-hive.md | Covered inhdinsight-using-json-in-hive.md
| Sample examples in GitHub* |  |  | Y | Y | P1 | [5 empty] | hdinsight-hive-analyze-sensor-data.md AND hdinsight-analyze-flight-delay-data-linux.md | Do our updates to hdinsight-hive-analyze-sensor-data.md and hdinsight-analyze-flight-delay-data-linux.md address this? | check our sample code into our existing private repo
Developing Spark apps (P0)
| Spark Overview |  |  |  |  | P0 | Y |  |  |  |  | hdinsight-spark-scenarios.md |  | Like ETL overview, can we create a new scenario for this (could use ML or streaming). Motivates the use of spark
| Running Spark from Shell* |  |  | Y |  |  | Y |  |  |  |  | hdinsight-spark-shell.md
| Running Spark from notebook* |  |  | Y | [6 empty] | Y | hdinsight-apache-spark-jupyter-notebook-kernels AND hdinsight-apache-spark-zeppelin-notebook | Covered by hdinsight-apache-spark-jupyter-notebook-kernels AND hdinsight-apache-spark-zeppelin-notebook
| Running Spark from IntelliJ* |  |  | Y | [6 empty] | Y | hdinsight-apache-spark-intellij-tool-plugin | Covered by hdinsight-apache-spark-intellij-tool-plugin
| Debug spark apps by setting up VPNs* |  |  | Y | [6 empty] | Y | hdinsight-apache-spark-intellij-tool-plugin-debug-jobs-remotely | Covered by hdinsight-apache-spark-intellij-tool-plugin-debug-jobs-remotely | New feature in IntelliJ enables remote debugging. So deprecate this articl and refer to blog post about debuggin with IntelliJ
| Writing Spark application using Scala, Java, Python* |  |  | Y | Y | [7 empty] | What should be covered? Need more details.
| Configuring Spark settings |  |  |  | Y | P0 | [6 empty] | What should be covered? Need more details. | Cover the articles sent by Maxim (TR and channel 9 links)
| Sample examples in GitHub |  |  |  | Y | P1 | [6 empty] | How to address?
Developing SparkML apps (P0)
1 | Creating SparkML pipelines* |  |  | Y |  |  | Y |  |  |  |  | hdinsight-creating-spark-ml-pipelines.md
2 | Creating SparkML models in notebooks* |  |  | Y | [6 empty] | Y | machine-learning/machine-learning-data-science-process-scala-walkthrough
3 | Sample examples in GitHub* |  |  | Y | Y | P2 | [6 empty] | How to address?
Spark SQL and Spark GraphX graph (P0)
| Deep learning | [9 empty] | Y | hdinsight-deep-learning-caffe-spark.md | Covered by hdinsight-deep-learning-caffe-spark
| Talk to Maxim and Xiaoyong |  |  |  | Y | [7 empty] | Any additional details?
Developing R scripts on HDInsight (P0)
| ML and Deep Learning |  |  |  | Y | [7 empty] | What should be covered? Need more details. | Cover whatever is sent by Xiaoyong
| What is R Server? | [9 empty] | Y | hdinsight-hadoop-r-server-overview.md
| Configuring R server on Spark |  |  |  | Y | [7 empty] | What should be covered? Need more details.
| Benefits of R server on Spark vs. R Server on Hadoop | [5 empty] | Y |  |  |  |  | hdinsight-hadoop-r-server-compute-contexts.md | Covered in hdinsight-hadoop-r-server-compute-contexts
| Analyzing your R data from WASB/ADLS | [9 empty] | Y | hdinsight-hadoop-r-server-storage.md | Covered by hdinsight-hadoop-r-server-storage
| Submitting jobs from Visual Studio Tools for R* |  |  | Y |  |  | Y |  |  |  |  | hdinsight-submit-jobs-from-r-tools-for-vs.md
| Submitting R jobs from R Studio Server* |  |  | Y |  |  | Y |  |  |  |  | hdinsight-submit-jobs-from-r-studio-server.md
Developing Spark Streaming apps (P0) | [12 empty] | Is the R server in this a typo?
| What is Spark Streaming? | [5 empty] | Y |  |  |  |  | hdinsight-spark-streaming-overview.md
| What is Spark structured streaming? | [5 empty] | Y |  |  |  |  | hdinsight-spark-structured-streaming-overview.md
| Creating Highly Available Spark Streaming jobs in Yarn |  |  |  | Y | P0 | [6 empty] | Can team provide more details on what should be covered here?
| Creating Spark Streaming jobs with exactly once event processing guarantees | [5 empty] | Y |  |  |  |  | hdinsight-spark-streaming-exactly-once.md
| Connecting Spark Streaming and Structured Streaming Jobs to Kafka * |  |  | Y | Y | P1 |  |  |  |  | Y | hdinsight-apache-kafka-spark-structured-streaming AND hdinsight-apache-spark-with-kafka | For Structured Streaming, this is covered by hdinsight-apache-kafka-spark-structured-streaming AND for Spark Streaming this is covered by hdinsight-apache-spark-with-kafka (the latter notebook needs to be updated for Spark 2.1) | update to Spark 2.1
| Connecting Spark Streaming and Structured Streaming jobs to EventHubs* |  |  | Y |  | P1 | Y |  |  |  |  | hdinsight-apache-spark-eventhub-streaming AND hdinsight-spark-structured-streaming-from-event-hubs.md | For Spark Streaming, this is covered by hdinsight-apache-spark-eventhub-streaming. For Structured Streaming, we wrote up hdinsight-spark-structured-streaming-from-event-hubs.md
| Connecting Spark Streaming and Structured Streaming jobs to PowerBI* |  |  | Y | Y | P1 | [6 empty] | For Power BI from Spark Streaming / Structured Streaming, what library should be used? The Microsoft one no longer appears in Maven and the community one was only updated thru Spark 1.5. | Skip
| Publishing real time updates to PowerBI |  |  | Y | Y | P1 | [6 empty] | Is this a duplicate of above? | Skip
|  |  |  | SUMMARY: | P0 | 12
[5 empty] | P1 | 8